## WBS
Task Group | Task | Assign | From | To | % completed | Note | Project | quản lý tiệc cưới
Project Management | Họp với khách hàng | A | 2020-04-17 | 2020-04-17 | 0% |  | Resource | 3 người | A, B, C
Project Management | Họp team để triển khai | Team | 2020-04-17 | 2020-04-17 | 0% |  | Time | 1 Tháng
Project Management | Viết spec | [5 empty] | Họ tên | Trần Văn Tâm, Nguyễn Trung Kiên, Nguyễn Hữu Phúc
| module admin | B | 2020-04-18 | 2020-04-18 |  |  | MSSV | 17DH111036
| module bán hàng | C | 2020-04-18 | 2020-04-18
Project Management | Meeting review | Team | 2020-04-18 | 2020-04-18 | 2%
Project Management | Approve spec | Khách
Project Management | Viết plan | A | 2020-04-19 | 2020-04-19 | 4%
code
Project Implementation | Admin
| Quản lý user (DB + UI) | A | 2020-04-20 | 2020-04-21
| Đăng nhập (DB + UI) | A | 2020-04-20 | 2020-04-21
| Quản lý đơn đặt tiệc (DB + UI) | B | 2020-04-20 | 2020-04-21
| Các báo cáo liên quan | C | 2020-04-20 | 2020-04-21
| Tra cứu danh sách tiệc cưới | C | 2020-04-20 | 2020-04-21
Project Management | Review + chỉnh sửa | Team | 2020-04-22 | 2020-04-22 | 30%
Project Implementation | User
| Home page: Thông tin, sảnh tiệc, Thực đơn, dịch vụ | A | 2020-04-23 | 2020-04-24
| Trang chi tiết sảnh tiệc, thực đơn, dịch vụ | C | 2020-04-23 | 2020-04-24
| Đơn đặt hàng | B | 2020-04-23 | 2020-04-24
| Fix bug | Team | 2020-04-25 | 2020-04-25
Project Management | Họp team + review | Team | 2020-04-26 | 2020-04-26 | 60%
CM Management | Chuẩn bị môi trường server | A | 2020-04-27 | 2020-04-27 | 70%
CM Management | Phân quyền người sử dụng | A | 2020-04-28 | 2020-04-28 | 75%
Project Implementation | Tester kiểm thử hệ thống | D | 2020-04-29 | 2020-04-30
Project Implementation | Kiểm thử cuối cùng với khách hàng | Team + Khách hàng | 2020-05-01 | 2020-05-01 | 80%
CM Management | Cài đặt môi trường | A | 2020-05-02 | 2020-05-03 | 90%
Project Implementation | Chuẩn biị tài liệu hướng dẫn cho khách hàng | B | 2020-05-03 | 2020-05-03 | 99%
Project Implementation | Đóng gói | C | 2020-05-03 | 2020-05-03 | 99%

## Risk Mgmt
No | Risk | Risk Description | Risk Type | Risk Group | Affects | Probability | Exponent | Strategy Type | Strategy Description
1 | Ngôn ngữ lập trình | Ngôn ngữ mới tiếp cận | Technology | C4 - Environment | 1 | 10% | 0.1 | Minimize Affects | Cố gắng vừa học vừa làm
2 | Thiếu nhân sự | Không đủ nhân viên | People | C1 - Customers & Users | 1 | 10% | 0.1 | Minimize Affects | Mỗi người sẽ cố gắng 200%
3 | Yêu cầu không ổn định | Khách hàng yêu cầu không rõ ràng, hoặc thay đổi thường xuyên | People | C2 - Scope & requirement | 2 | 25% | 0.5 | Minimize Affects | Cần phải gặp khách hàng xác định lại rõ yêu cầu
4 | OT | Bị ép làm thêm giờ | People | C3 - Execution | 1 | 10% | 0.1 | Avoid Risk | Lãnh đạo cần phải thêm tí lương cho nhân viên
5 | Không đáp ứng yêu cầu thời gian thực | Không hoàn thành đúng thời gian được giao | People | C1 - Customers & Users | 2 | 25% | 0.5 | Plan B | Gặp mặt khách hàng xin thêm giờ
6 | [6 empty] | 0
7 | [6 empty] | 0
8 | [6 empty] | 0
9 | [6 empty] | 0
10 | [6 empty] | 0
11 | [6 empty] | 0
12 | [6 empty] | 0
13 | [6 empty] | 0
14 | [6 empty] | 0
15 | [6 empty] | 0

## Ref
Risk group | Mức độ rủi ro | Xác suất rủi ro | Task Group | Risk type | Strategy Type | Member | note
C1 - Customers & Users | 1 | 10% | Project Management | Technology | Avoid Risk | A | Ghi chú 1
C2 - Scope & requirement | 2 | 25% | CM Management | People | Minimize Affects | B | Ghi chú 2
C3 - Execution | 3 | 50% | Training | Organizational | Plan B | C | Ghi chú 3
C4 - Environment | 4 | 75% | Project Implementation | Tool |  | Team | Ghi chú 4
| 5 | 100% | Package and Release | Requirement |  | Khách
|  |  |  | Estimation |  | D
|  |  |  | Execution |  | Team + Khách hàng